# The 90-day plan: one page the board can approve

Every version of the board memo asks for the same thing: approval for a costed 90-day plan, with a named owner per area and a report back in 12 months. This is that plan. Fill it in before the meeting, not after. A board approves a plan far quicker than it approves an idea, and "here's exactly what I'd do" closes a discussion that "we should do something" leaves open.

The rules that keep it credible:

Three drivers, not eight. Take your three weakest from the Scan or the intervention menu. Spreading a first effort across everything is how it dies. Fix the worst first, prove it, come back for more.

One lead action each, pulled straight from the intervention menu. Every action on that menu carries published evidence and none of it is a perk. Don't invent your own. The point is that you can name the source when someone asks.

A proof measure per action, agreed up front. Decide now how you'll know it worked: absence rate, voluntary turnover, decision turnaround, the re-run driver score. Write down today's figure for each, so you can show movement later. A plan with no measure is a wish.

A named human owns each one. Not "HR" or "the leadership team". A name.

## The plan

Organisation: [Name] Sponsor: [Name, role] Start date: [Date] Report back: [Date, around 12 months]

| Weakest driver | Lead action (from the intervention menu) | Owner | Cost | Proof measure (and today's figure) | By day 30 | By day 60 | By day 90 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| [DRIVER 1] |  |  | £ |  |  |  |  |
| [DRIVER 2] |  |  | £ |  |  |  |  |
| [DRIVER 3] |  |  | £ |  |  |  |  |

Total 90-day budget requested: £[BUDGET] Re-assessment: re-run the WellbeingROI Scan at 12 months and report the moved scores, absence rate and turnover to the board.

## Worked example: one row filled in

So you can see the level of detail a board wants. This uses the single strongest-evidenced action in the field.

| Weakest driver | Lead action | Owner | Cost | Proof measure | By day 30 | By day 60 | By day 90 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Support & Leadership | Four-hour mental-health training for every people manager (Milligan-Saville et al., Lancet Psychiatry, 2017; cluster randomised trial, roughly £10 returned per £1 spent) | [HR lead] | Trainer day rate plus manager time | Sickness absence rate (the trial's own outcome) and return-to-work interview quality | Training booked, managers scheduled | All managers trained | First absence read at 90 days against baseline |

## This plan is also your evidence

The plan does a second job. Acting on what you find, and recording it, is exactly what the law expects of a stress risk assessment, and what ISO 45003 expects of managing psychosocial risk. Keep this page alongside your completed workbook. Together they show an inspector, or a board, that you found the risks and did something about them.

## The cost of waiting: put this line in your ask

A board that "notes it and revisits next quarter" isn't holding at zero. The leak runs the whole time.

Take your annual figure and divide by four. That's roughly what one more quarter of doing nothing costs.

Worked example: an annual leak of £619,236 is about £154,809 a quarter, the price of sitting on the decision for three more months. (Same conservative, part-modelled basis as your Scan figure; see the costs cheat sheet.)

Set that against a 90-day plan whose first action returns around £10 for every £1, and "let's wait" gets much harder to say.

## The honesty that makes it land

Build a stop point into the plan and say so out loud: if the measures don't move over the year, we stop. It costs you nothing, because the evidence says these actions work, and it turns your proposal from an open-ended commitment into a bounded, measured trial. Boards approve trials.

## Sources

- Milligan-Saville, J. et al. (2017). Lancet Psychiatry — four-hour manager mental-health training cut sickness absence in a cluster randomised controlled trial; roughly £10 returned per £1 spent.

- Deloitte (2024). Mental health and employers — return of £4.70–£6.30 per £1 invested in organisational wellbeing action.

- Management of Health and Safety at Work Regulations 1999, Regulation 3 — duty to assess and act on work-related stress risk; significant findings recorded where five or more are employed. legislation.gov.uk

- ISO 45003:2021 — guidelines for managing psychosocial risks at work. iso.org

- HSE Management Standards — the six areas your drivers map onto (Demands, Control, Support, Relationships, Role, Change). hse.gov.uk/stress/standards

- The £619,236 example and every cost constant behind it are set out in the costs cheat sheet in this kit, each one sourced or labelled modelled.

This plan is for decision support, not audited accounts.